## Intro
Weekly Project Tracking Spreadsheets
This file contains two sample project tracking sheets, one for individual contributors
and one for group managers
How to use this spreadsheet (for team members):
1 | Save with a file name in this format: Smith John 20080618 (for week ending June 18th, 2018).
2 | Fill out with all of your responsibilities, both long term projects and short term tasks.
3 | Update the file during the week.
4 | When you complete a task, just move it below the green line.
5 | Each Friday, send it back to your manager..
6 | On Monday, save a new version of the file with the following Friday's end date.
7 | Erase all completed tasks from the prior week.
8 | Rinse and repeat.

## Timesheet-Project-Team-Member
Weekly Project Tracking
Name: Jericho C Siahaya |  | PM Team Gesit - Ismahan Chaerunnisa | Role | Developer - Backend |  | Week End: | 2021-07-30
Priority (1- 4) | Task |  | Target Hours | Time to Complete | Deadline | Risk Factors | Requiring Mgr Attention | Orginal Est. (Hrs) | Hrs Used To Date | Est. Total Needed to Complete | % Overrun (Underrun)
Tasks in Progress
1 | Membuat rancangan database Gesit |  | 3 | 3 | 24/8/2021 |  |  | 160 | 130 | 133 | -16.88%
Completed Tasks
1 | Membuat webview aplikasi mobile |  | 2 | 2 | 19/7/2021
2 | Membuat API login |  | 3 | 2 | 26/7/2021
Total |  |  | 8 | 7 |  |  |  | 160 | 130 | 133 | -16.88%
Plans for Next Week
Membuat rancagan ERD untuk fungsi notifikasi
Comments

## Timesheet-Project-Manager
Weekly Project Tracking
Name: |  | PM - [Name_Of_PM] | Title: | Project Manager |  | Week End: | ________________________________ | ________________________________
Priority (1- 4) | Task |  | Owner | Support | Deadline | Status | Risk Factors | Requiring Mgr Attention
Tasks in Progress
|  |  | David | Scott
Completed Tasks
Total |  |  | 0 | 0
Plans for Next Week
Comments